## Sheet1
Karui Changes			Details	Responsible	Est time to completion	Confidence level
Integrated electronics
	Internal PS	Yes	Meanwell 500W – Switch mounting in case for the 500W	Chris		Integrate Internal Power Supply
	Integrated LCD	Yes	Same LCD – possible better grounding	Chris
	esd changes – rrd	Maybe	Chris will get in touch with rrd about esd changes	Chris
	reset switch on front	Maybe	Need to check with marketing and source	Chris
	LCD workflow	Yes	One more round with marketing	Patrick
	Move Plugs to back and Fan	Yes	Plugs good, move fan	Julie
	get mktg. Approval on case	Yes	Make up rendering / mockup of control box to get mktg approval	Julie
	New Board	Yes	New layout is needed after FCC testing	Chris
	No LCD back-power	Yes	In progress with the new board testing	Chris
	Z-Backup switches	Yes	We have the switches, still in testing	Chris
	FCC/CE	Yes	Class B with new board and PS	Chris

Auto-leveling		Yes	Testing In progress	Patrick
	0.50 Nozzle	Yes	Already integrated into TAZ line	Patrick
	Better wiper / lower	Maybe	Currently testing Nylon scrubber pad material	Patrick

Mechanical redesign
	Sheet metal sides / ctrl box	Yes	Need to design sheet metal sides and control box	Julie
	revised Extruder	Maybe	Something without spring screws and a significantly easier latch	Bam
	Dual Extrusion Fans	Yes	We just need to make sure splicing the fans together is a good way to go here	Bam
	Cable guides	Yes	Larger may be necessary, still need to solve y-axis	Bam
	Stainless Drive rods	Yes	Sticking with Misumi, will test SST and coated in 1st round prototypes	Bam
	Quieter fans	Maybe	quieter UL fans ordered, will test when delivered	Bam
	Min and Max switches (z)	Yes	integrate into z lower and x motor end	Julie
	Stiffer Axis for droop/bed warp	Yes	12mm x-rods, possible firmware compensation	Bam
	Tighter tolerance bushings	Maybe	Will test on 1st iteration of Kauri parts	Bam
	New Drive system in Z (IM)	Maybe	IM parts in progress, Need to test to justify 2nd Z rod	Julie
	New Drive system in Z (IM)	Maybe	Machined and printed replacement, need to justify 2nd z-rod	Bam
	Filament cleaner/wiper	Yes	Currently testing foam version	Seth
	Change the drive gear material	Maybe	Nylon gears being tested in cluster	Bam
	Cleaner/easier wiring	Yes	make wire harnesses easier to build. Don't combine multiple into one if possible	Bam
	Snap in y-axis	Yes	In testing	Bam
	Shippable mounted toolhead	Maybe	If secure enough, need to test	Bam
	Cubed volume	Yes	Currently 286mm cube	Bam

Injection molded parts		Yes	Should design plastic parts with this in mind	Julie
	analysis of parts to mold	Yes	Done, starting with bearing holder,	Julie

Marketing				Harris
	New Box	Yes	Something more conducive to retail shelving	Harris
	New Name	Yes	TAZ 6	Harris
	New Laser etching	Yes		Ben
	New document package	Yes		Harris

	Cost analysis of molding vs printing	No	Molding is essential and printed cost must be inaccurate	Julie
	Quieter motors	No	if needed / beneficial	Bam
	Change Switch color	No	Red is the way to go as per marketing	Seth
New Nozzle/All in one dual?		No	Maybe non-changeable, welded nozzle. Possibly all in one dual nozzle?
Thermal Fuse		No	Needs research
Lights		No	Do we need to add something onto the board for this?
Wifi module		No	Find/Test
Higher step settings		No	Testing new motor drivers
Change the Look		Yes
Easier to Assemble for customer		Yes	30 min box to print?
Less expensive		Yes
Easier to Assemble for manufacturing		Yes

## Sheet2
PP Listing		IM / Printed / machined	Assigned	Changing?	Notes	Percent Done
X axis
	Xend idler	IM	Julie	yes		30.00%
	X-end Idler backup	Printed +Sheet metal	bam	yes		30.00%
	X-end motor	IM	Julie	yes		30.00%
	X-end motor backup	Printed +Sheet metal	bam	yes		30.00%
	X-bearing holder(s)	Printed	bam	yes		30.00%
	X-carriage	Sheet metal	bam	yes		50.00%
	belt mount	Printed	bam	yes	Need to redraw in FreeCAD, thru holes instead of inserts	0.00%

Y axis
	Y-attachment	Printed	bam	yes	2 designed paths, need to choose between	95.00%
	Y-corners	IM	Julie	yes		90.00%
	Y-idler	Printed	---	no	Just needs FreeCAD redraw	75.00%
	Y-motor	Printed	---	no	Just needs FreeCAD redraw	75.00%
	Bed bearing holder	IM	Julie	Yes		90.00%
	Bed corner	Printed	bam	No		90.00%
	Belt / switch mount	Printed	bam	yes	redrawn, testing	95.00%
	Y-harness connection	Printed	bam	yes	Integrated into belt mount	95.00%

Z axis
	Z lowers	IM	Julie	Yes		50.00%
	Z-uppers	IM	Julie	Yes		50.00%
	Z min switch mounting	IM	Julie	Yes	Part of Z lower	30.00%
	Z-max switch mounting	IM	Julie	Yes	Part of x-end idler	30.00%

Printhead
	HB Gears	Printed	bam	maybe	Testing different materials, model will remain the same	90.00%
	Extruder body	Printed		no	Use current design	100.00%
	Extruder Latch	Printed		no	Use current design	100.00%
	Extruder mount	Printed	bam	yes	Redraw in freecad	30.00%
	Fan shrouds	Printed	bam	yes	Redraw in Freecad	0.00%
	Switch mounting	Printed	bam	yes	Part of extruder mount	0.00%

Sheet metal
	Left side	Sheet Metal	Julie	yes		20.00%
	Right Side	Sheet Metal	Julie	yes		20.00%
	Control box	Sheet Metal	Julie	yes		30.00%
	Bed Plate	Sheet Metal	Julie	yes		50.00%
	Y-motor plate	Sheet Metal	Julie	yes	Changing per marketing's request	50.00%
	Y-idler plate	Sheet Metal	Julie	yes	Changing per marketing's request	50.00%

Misc
	Wiper mount	Printed	bam	Maybe	Keep as is on the mini until machines are built up for testing	50.00%
	Nameplate	??	bam	Maybe		0.00%
	Control Box mounting	Printed	bam	No	Need to redraw in FreeCAD	50.00%
	Spool Arm	Printed		yes	Need to redraw in FreeCAD, make less sharp	0.00%
	Feed tube holder	Printed		yes	Need to redraw in FreeCAD, make less sharp	0.00%
	Feed tube spinner	Printed		No	Keep the same as it is currently	100.00%
	Filament cleaning system	???	Bam / Seth	Yes	Need concept design	0.00%

Sourcing
	Control box fan		bam	yes	Need to source UL, waiting on pelonis	30.00%
	Extrusion fan		bam	yes	Need to source UL, waiting on pelonis	30.00%
	Heatsink fan		bam	Maybe	Need to source UL, waiting on pelonis	30.00%
	Switch		Seth	Maybe	Change color? Probably not, green looks cool though	100.00%