## Sheet1
		09-28	10-05	10-12	10-19	10-26	11-02	11-09	11-16	11-23	11-30	12-07	12-14	12-21	12-28	01-04	01-11	01-18	01-25	02-01	02-08	02-15	02-22	02-29	03-07	03-14	03-21	03-28	04-04	04-11	04-18	04-25	05-02	05-09	05-16	05-23	05-30	06-06	06-13	06-20	06-27	07-04	07-11	07-18	07-25	08-01
																CES
TASKS	OWNER	EVT / Engineering Verification Test					Finish Ordering / DVT Parts	Wating for DVT Parts			DVT – Qualification / Design Verification Test								Finish Ordering / SAT Parts	Wating for SAT Parts			SAT – Qualification / Ship Approval Test		Production & Inventory Buildup		Finish Ordering / SAT Parts	Wating for SAT Parts			SAT – Qualification / Ship Approval Test
R&D – Mechanical	Brent M
Finalize BOM for DVT	Brent M
Finalize BOM for SAT	Brent M
Get product specs to Marketing	Brent M
Continue Development of IM parts	Julie P
R&D Electrical	Patrick
Feature list for Avon
Connector list for Avon
New Avon layout
LCD menu structure	Patrick
Firmware	Patrick / Eric
Software	Nick T
Cura profiles	Brent M
Any needed Cura changes	Nick T
Build & Test	Julie P
Built and test EVT printers	Brent M
Finish Test & Qualification Plans	Julie P
Heatsink Fan Testing	Julie P
Acoustics Testing	Julie P
Drop Testing	Julie P
Thermal Testing	Julie P
Fan lifetime testing	Julie P
EMC test with EVT printer	Eric
Final EMC testing on Production printer	Eric
Test bed leveling on TAZ	Patrick
Test final firmware/software configuration	Patrick
Packaging / Documentation	Ben
Foam design	Brent M											6-8 weeks, additional 1-2 if there are changes
Packaging Design	Ben
User Manual	Brent I.
Documentation	Claudio?
Procurement	Brent M
Camellia (DVT/SAT) Parts
Production Parts – Long lead
Order parts for 20 DVT Printers	Brent M
Order long lead production parts	Brent M
Order short lead production parts	Brent M
Plastic Parts	Stan
Manufacturing	Micky
Process step define (presub-FA)
Process step layout
Assembly line layout & BOM
Mfg line 2 construction/ purchase
Resource Plan proposal/ approval
Recruiting mfg staffs
Training new team
Build 20 of the DVT printers	Micky
Build 30 of the SAT printers	Micky
Design/Build up any fixturing needs for Assembly	Micky
Build production	Micky / Bob
Assembly OHAI Kits	Micky
PreSub Op setup & production prep
Cycle time modeling
Presub/Sub Test Defined
Pre/Sub Test Equip Des/Setup
- Harness Test Fixture
- Other fixtures
MO
Marketing / PR / Sales / CS	Harris
Final Product Photos	Ben
Finalize Laser etching & machine colors	Ben
Product Pages	Harris
Customer support training	Brent I.
Product Description	Harris
Product name	Harris
EVT laser etch concept	Ben
Printers for review	Harris