## Sheet1
Category	AO Part #	Description	Manufacturer	Manufacturer PN	Distributor	Distributor SKU	Qty Per	UOM	Price Per Unit	Price Total	Qty to Order	PO	Date	ETA	NOTES
										$105.32	3050
Electronic	EL-CA0030	6ft 18AWG Power Cord Cable w/ 3 Conductor PC Power Connector Socket (C13/5-15P) – Black			Linvox		1	ea	$1.10	$1.10	3050	PO08359	06/30/15	09/02/15	confirmed
Electronic	EL-MS0143	Conn Fast Receptacle14-16 AWG .250 (2200 Unit Reel)		3-350819-2	Tti	3-350820-2	9	ea	$0.069	$0.62	27450	PO08369	06/30/15	09/01/15	confirmed
Electronic	PP-MP0028	AC Power Entry Modules SC MT FUSED .25" TAB			Heilind	161-PF0030/63	1	ea	$2.69	$2.69	3050	PO08370	07/01/15	10/06/15	800 ship 9/29 2950 ship 10/5 per heilind
Electronic	EL-MS0096	Cartridge Fuses 125V 7A 5X20 MA UL LBC			Digi-Key / TTI	576-0233007.MXP	2	ea	$0.45	$0.89	6100	PO08371	07/01/15	See Notes	delivered
Electronic	EL-MS0248	CONN RING 14-16 AWG #10 PIDG	TE	2-36160-1	Digikey / TTI	A1072TR-ND	7	ea	$0.098	$0.68	21350	PO09789			Ordered 9/29, digikey stock can ship overnight
Electronic	EL-PS0031	Mean Well Switching Power Supplies 504W 24V 21A Power Supply W/PFC	Mean Well	RSP-500-24	Sager	709-RSP500-24	1	ea	$65.00	$65.00	3050	PO08321	06/30/15	See Notes	Scheduled Delivery – 800 units per month until 8/2016
Electronic	EL-WR0106	16AWG Stranded – Red		C2065A.21.03	Allcable	HU15691626RD	520	mm	$0.000	$0.15	1586000	PO08457	07/07/15	09/04/15	6K
Electronic	EL-WR0121	16AWG Stranded – Black		HU15691626BK	Allcable	HU15691626BK	380	mm	$0.000	$0.11	1159000	PO08457	07/07/15	09/04/15	4K
Electronic	EL-WR0124	16AWG Stranded – Green w/ yellow stripe			Allcable		140	mm	$0.000	$0.05	427000	PO08457	07/07/15	09/04/15	2K
Electronic	EL-WR0123	16AWG Stranded – White		HU15691626WE	Allcable	HU15691626WE	190	mm	$0.000	$0.05	579500	PO08457	07/07/15	09/04/15	2k
Electronic	EL-MS0246	Conn Ring 16-22 AWG #4 Red PIDG			Digikey	A27229CT	2	ea	$0.449	$0.90	6100	PO08371	07/01/15	09/01/15	delivered
Electronic	EL-CA0073	Multi-Conductor Cables 14AWG 4C UNSHLD, BLACK	Belden Wire & Cable	1310A 010U500	Allcable	566-1310A-U500-10	1000	mm	$0.00	$2.76	3050000	PO07924	06/10/15	07/31/15	Delivered 305,000/304.8=10,006.562Feet
Electronic	TL-CS0136	Flame-Retardant Heat-Shrink Tubing, 0.21" ID Before Shrinking, 25' Long			Fastenal	7864K32	80	mm	$0.00	$0.09	244000	PO08442	07/09/15	09/03/15
Electronic	EL-MS0249	Front Mount Male, 4 pin, solder			WEIPU	SP2112/P41N	1	ea	$1.87	$1.87	3050	PO07963	06/12/15	07/31/15
Electronic	EL-MS0250	Cable connector female, 4 pin, solder			WEIPU	SP2110/S4II1N	1	ea	$1.87	$1.87	3050	PO07963	06/12/15	07/31/15
Electronic	EL-SW0023	SWITCH ROCKER DPST 20A 250V, illuminated red			Digikey/Heilind	EG1535-ND	1	ea	$1.570	$1.57	3050	PO08299	06/25/15	09/02/15	13 Week lead time on this part. - Tsimspon
Hardware	HD-MS0290	Mil. Spec. Grommet, Fits 9/16" Diameter Hole & 1/16" Thick Panel, MS-35489-9			Fastenal	9307K16	1	ea	0.12	$0.12	3050	PO08442	07/09/15	09/03/15
Hardware	HD-BT0155	Black Alloy Steel Flat-Head Socket Cap Screw, Class 10.9, M4 Size, 6mm Length, .70mm Pitch			Fastenal	91294A186	4	ea	0.01	$0.04	12200	PO08442	07/09/15	09/03/15
Hardware	HD-MS0289	Nylon Loop Clamp, 5/16" ID, Black			Fastenal	8876T37	1	ea	0.0298	$0.03	3050	PO08442	07/09/15	09/03/15
Hardware	HD-WA0035	Metric 18-8 Stainless Steel External Serrated Lock Washer, M3 Screw Size, 6mm OD, 0.4mm min Thick			Fastenal	91120A120	1	ea	$0.018	$0.02	3050	PO08442	07/09/15	09/03/15
Hardware	HD-MS0288	Adhesive-Back Bumper, Tapered, Polyurethane, 1/2" Wide, 15/64" High, Black			Fastenal	95495K24	4	ea	$0.099	$0.40	12200	PO08442	07/09/15	09/03/15
Hardware	HD-BT0128	M3 x 6 Bolt, FHCS Black-Oxide			Fastenal		10	ea	$0.037	$0.37	30500	PO08442	07/08/15	09/03/15
Hardware	HD-NT0001	M3 Nyloc Nut, Zinc Plated			Fastenal		2	ea	$0.01	$0.01	6100	PO08442	07/08/15	09/03/15	100/pk
Hardware	HD-WA0001	M3 Washer, Steel, Zinc Plated		MTR-M3100321	Fastenal	MTR-M3100321	2	ea	$0.00	$0.02	6100	PO08442	07/08/15	09/03/15
Mechanical	PP-MP0096 – PP-MP0104	Upper PS case, RSP			Star		1	ea	$7.110	$7.11	3050	PO08009, 08013, 08024, 08025, 08027, 08028	See notes		Scheduled deliveries: 600 units 8/3 – 500 units on the following dates: 8/24 – 9/14 – 10/5 – 11/2 – 12/1 (Laser Etching PO08014)
Mechanical	PP-MP0097 – PP-MP0103	Lower PS case, RSP			Star		1	ea	$16.270	$16.27	3050	PO08009, 08013, 08024, 08025, 08027, 08028	See notes		Scheduled deliveries: 600 units 8/3 – 500 units on the following dates: 8/24 – 9/14 – 10/5 – 11/2 – 12/1 (Laser Etching PO08014)
Electronic	EL-MS0254	FERRITE BRDBAND CYLINDER 17.07MM – 28B0672-000			Digikey	28B0672-000	1	ea	0.26013	$0.26	1800	PO08371	07/01/15	09/21/15	confirmed deliver 687 qty 9/1 1113 qty 12 wks 9/21 expediting will advise improved delivery date
Electronic	EL-MS0259	HEATSHRNK DL WL Q53X 3/4"X4'BLK			Digikey	Q53X034B-ND	0.0666666667	ea	4.116	$0.27	125	PO08371	07/01/15	09/01/15	confirmed

		Solder
		Laser etching

		Allcable – Cable Assembly delivery dates Please see following schedule: / June 12th - 100 of each / June 19th- 350 per week - Our goal would be to be done with the next 1700 within 5 weeks.				Don't order yet
						Items that can be ordered
						We have enough/on order

		Description	End	Wire	Color	Length	End
		Ground wire from Inlet to Stud	EL-MS0143	EL-WR0124	Green w/ Yellow	60mm	EL-MS0246
		Ground wire from Stud to PS	EL-MS0246	EL-WR0124	Green w/ Yellow	60mm	EL-MS0248
		Neutral line from Inlet to Switch	EL-MS0143	EL-WR0121	Black	70mm	EL-MS0143
		Neutral line from Switch to PS	EL-MS0143	EL-WR0121	Black	100mm	EL-MS0248
		Live line from Inlet to Switch	EL-MS0143	EL-WR0123	White	70mm	EL-MS0143
		Live line from Switch to PS	EL-MS0143	EL-WR0123	White	110mm	EL-MS0248