## Sheet1
06/16/14	06/23/14	06/30/14	07/07/14	07/14/14	07/21/14	07/28/14	08/04/14	08/11/14
Build/test EVT-2		Design Case around electronic choices	Order DVT parts – this is just long enough to get un-plated sheet metal			Build DVT – This is a 6 week schedule push		Order SAT parts
Things that need to be accomplished:		Get DVT BOM finished	Build up, EVT-2s as close to DVTs as we can for testing
Full testing on Core Board		Verify parts we need to order
Full testing on Mini RAMBo
LCD chosen and tested
LED/Driver board chosen and tested
Power control chosen and tested
Nozzle selection Finished

Build qty notes:
This schedule is based on using mostly the parts that we already have.
We should build 5 EVT-2s
We will then build 10 DVTs
That will make it so we don't need to order more long lead parts like motors and drive rods.