## Sheet1
			LulzBot Mini – Product Development Cycle – v3.2
			08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01	12-08	12-15

TASKS		OWNER	EVT / Engineering Verification Test / (Begonia)					DVT/SAT – Qualification / Design Verification/Ship Approval Test / (Camellia)					Production & Inventory Buildup / (Daffodil)		CYBER Monday	Production & Inventory Buildup / (Daffodil)
R&D – Mechanical		Seth
Frame- finalize design/ order DVT		Seth
Nozzle- retention		Brent
Bed Mounting – Z corner		Brent
PEI		Brent				PEI		Done		New adhesive eval
Quik-exchange Print head design		Seth/ Brent						Done
Drive Rod		Seth
X-End Re-design		Seth						Done
Final BOM		Seth
R&D Electrical		Seth
Wire/cable/harness		Seth/Brent						Done
Z-Overrun Sw		Seth
Thermal Cutoff verifiy		Brent						continue monitoring
Switch Interference								saw once		continue monitoring
Software		Steven
SW package selection		Steven
Open SW		Steven
Bug testing		Steven
GUI changes		Steven
Print Profiles		Brent/Steven
Packaging

Code Release		Steven						DVT/SAT				Production
Build & Test		Seth
Test Plan		Seth/ Chris
Build Prototypes/ Test machines		Seth/ Brent
Functional		Seth/ Brent
Speed		Seth/ Brent
Mechanical Performance		Seth/ Brent
Useability		Seth/ Steven
Environmental		Seth/ Brent
Op-Shock		Seth/ Brent
Non-Opshock		Seth/ Brent
EMC		Seth
Long Term Reliability		Seth/ Stan
Packaging/ Documentation		Steven
Machine for foam prototype		Seth
Shipping Foam		Steven						Done
Final Foam design verify		Steven						Done
Internal Drop Test								Done
Fed-EX Test		Steven						Done
Boxes								Done
Operation Manual		Steven
- 16-Page PDF		Steven
Consumer's Open Box Exp Test		Steven
Procurement
Camellia (DVT/SAT) Parts		Seth/ Toni						Done
Production Parts – Long lead		Seth/ Jeff
Production Parts		Toni						sheet metal, PEI
Plastic		Chris/ Stan						Extended
Manufacturing		Chris
Process step define (presub-FA)		Seth/ Chris	1st pass
Process step layout		Chris
Assembly line layout & BOM		Chris
Mfg line 2 construction/ purchase		Andy/ Chris
Resource Plan proposal/ approval		Chris/ Jeff
Recruiting mfg staffs		Chris
Training new team		Chris
Build DVT/SAT Camellia machines		Chris
Assembly OHAI Kits		Seth/Robert
PreSub Op setup & production prep		Chris
Cycle time modeling		Chris	1st pass
Cycle time verification/ Opti		Chris						Extended
Optimize MFG process		Chris
Presub/Sub Test Defined		Chris						Done
Pre/Sub Test Equip Des/Setup		Chris
- Harness Test Fixture		Brent
- Other fixtures
MO		Chris
Marketing / PR		Harris
Frame Design		Kevin/Natasha
Customer Survey		Natasha/Harris
Market Research Review		Harris
Product Packaging		Kevin/Natasha
Teaser Package		Marketing (All)
Press Engagement		Harris/Schwartz
LulzBot.com/Mini Landing Pg.		Marketing (All)
LulzBot.com/Rocktopus Landing Pg.
Reseller Engagement		Rachael/Ben
Product Collateral Design		Kevin/Claudio
Final Product Photos		Kevin
Product Description		Harris/Natasha