## Sheet1
			Lulzbot Mini – Product Development Cycle – v3.2
			08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01	12-08	12-15

TASKS		OWNER	EVT / Engineering Verification Test / (Begonia)					DVT/SAT – Qualification / Design Verification/Ship Approval Test / (Camellia)					Production & Inventory Buildup / (Daffodil)		CYBER Monday	Production & Inventory Buildup / (Daffodil)
R&D – Mechanical		Seth
Frame- finalize design/ order DVT		Seth
Nozzle- retention		Brent
Bed Mounting – Z corner		Brent
Glue procedure		Brent
Quik-exchange Print head design		Seth/ Brent

Final BOM		Seth
R&D Electrical		Seth
Wire/cable/harness		Seth/Brent
Z-Overrun Sw		Seth
Thermal Cutoff verifiy		Brent

		Seth
Software		Steven
SW package selection		Steven
Bug testing		Steven
Print Profiles		Steven
		Steven
		Steven
		Steven
Code Release		Steven						Final code
Build & Test		Seth
Build Prototypes/ Test machines		Seth/ Brent
Functional		Seth/ Brent
Speed		Seth/ Brent
Mechanical Performance		Seth/ Brent
Useability		Seth/ Steven
Environmental		Seth/ Brent
Op-Shock		Seth/ Brent
Non-Opshock		Seth/ Brent
EMC		Seth
Long Term Reliability		Seth/ Stan
Packaging/ Documentation		Steven
Machine for foam prototype		Seth
Shipping Foam		Steven
Final Foam design verify		Steven
Fed-EX Test		Steven
Unbox Manual		Steven
Operation Manual		Steven
Consumer's Open Box Exp Test		Steven
		Seth

Procurement
DVT/SAT Parts		Seth/ Jeff
Production Parts – Long lead		Seth/ Jeff
Production Parts – short lead		Seth/ Jeff
Plastic		Chris/ Stan
Manufacturing		Chris
Process step define (presub-FA)		Seth/ Chris	1st pass
Process step layout		Chris
Assembly line layout & BOM		Chris
Mfg line 2 construction/ purchase		Andy/ Chris
Resource Plan proposal/ approval		Chris/ Jeff
Recruiting mfg staffs		Chris
Training new team		Chris
Build DVT/SAT Camellia machines		Chris
Assembly OHAI Kits		Seth/Robert
PreSub Op setup & production prep		Chris
Cycle time modeling		Chris	1st pass
Cycle time verification		Chris
Optimize MFG process		Chris
Presub/Sub Test Defined		Chris
Pre/Sub Test Equip Des/Setup		Chris
OpenERP Routing		Chris
Marketing / PR		Harris
Frame Design		Natasha
Customer Survey		Harris
Market Research Review		Harris
Product Packaging		Natasha
Reseller Preview		Harris
Product Photos		Emily
Product Collateral Design		Harris
Product Description		Harris
Press Prioritization		Harris
Press Engagement		Harris