## Log
Serial Number where implemented is required only during significant changes

Project:			Mini- Foxglove		Project release date:		July 4, 2016
ECO #	Change Type	ECO Date	Description of Change	Item impacted / (Pn, file, etc.)	New Item / (Pn, file, etc.)	Serial Number or Date implemented	LulzBot Material Disposition
			ECO tracking was implemented post project release
			ECO's listed occur on or after the noted Project release date noted
1	Part Design	07/05/16	New Printed part added to BOM, Item is a USB port protector	N/A		07/05/16	N/A
2	Part Design	07/05/16	New Printed part added to BOM, Item is a Bed Harness mount clip	N/A		07/05/16	N/A
3
4
5
6
7
8
9
10

## Change Notifications
Action from Change	Purchased off the shelf item	Purchased make to AO print item	Printed/ Made in house item	Task Owner
New Part Number	Create PN in ERP	Create PN in ERP	Create PN in ERP	Purchasing
	Update BOM	Update BOM	Update BOM	??? (Mfg Eng. Am I taking over BOM control?)
	Create new retail part?	Create new retail part?	Create new retail part?	Purchasing
	Purchase new item	Purchase new item		Purchasing
	Pull MSDS, provide to Facilities			Purchasing
		Create new part model & drawing	Create new part model & drawing	R&D
			Create Slice and gcode	R&D???
	Update Downloads	Update Downloads	Update Downloads	???
	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Warehouse
	Create new Inspection plan	Create new Inspection plan		Quality Manager
	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	Mfg Eng

	Purchased off the shelf item	Purchased make to AO print item	Printed/ Made in house item	Task Owner
Existing part modification	Update PN in ERP	Update PN in ERP	Update PN in ERP	Purchasing
	Update BOM	Update BOM	Update BOM	??? (Mfg Eng. Am I taking over BOM control?)
	Revised retail part?	Revised retail part?	Revised retail part?	Purchasing
	Purchase new item	Purchase new item		Purchasing
	Pull MSDS, provide to Facilities			Purchasing
		Revise part model & drawing	Revise part model & drawing	R&D
			Create Slice and gcode	R&D ???
	Update Downloads	Update Downloads	Update Downloads	???
	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Apply material disposition (scrap, rework, UAI) to stock items	Warehouse
	Revise Inspection plan	Revise Inspection plan		Quality Manager
	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	review OHAI (update PN references if any, check form factors)	Mfg Eng

BOM item change				Task Owner
	Temporary Deviation of PN or Quantity of part	Update purchasing plan for both parts, single part increase

	Change from one existing part to another	Update purchasing plan for both parts

	ECO #	Change Type	ECO Date	Description of Change	Item impacted / (Pn, file, etc.)	New Item / (Pn, file, etc.)	Serial Number or Date implemented	LulzBot Material Disposition

	TAZ 6.0 -Olive

## Action Template
Project:
ECO#
Change:
Old item	Old Qty	New Item	New Qty	Old Item Disposition
EL-SW0033	4	EL-SW0333	2	Scrap

Task				Action Owner
Create PN in ERP				Purchasing
Update BOM				??? (Mfg Eng. Am I taking over BOM control?)
Create new retail part?				Purchasing
Purchase new item				Purchasing
Pull MSDS, provide to Facilities				Purchasing
Create new part model & drawing				R&D
Create Slice and gcode				R&D???
Update Downloads				???
Apply material disposition (scrap, rework, UAI) to stock items				Warehouse
Create new Inspection plan				Quality Manager
review OHAI (update PN references if any, check form factors)				Mfg Eng