## Sheet1
EasyTAZ – WORK BREAKDOWN STRUCTURE

Architect
	Cube or Lulzbolt?
	- CAD
	- Build mockups
	- Cost estimate
	Electronics – Controller & Comm.
	- Research features
	- Research Market trends
	- Pros & Cons on FW effort
	- Final Config/feature proposal
	UL or Not UL or Partial UL for future Full UL?
	- Define what need to be done per choice.
	Cost estimates
Software
	SW Feature List
	BBB – LCD touch
	BBB – WiFi
	BBB – Smart Phone
	BBB – USB
	BBB – Camera
	User Interface Menu Diagram & Coding
	Interface Controls (Touch Screen)
Firmware
	RAMBO – SD
	RAMBO – BBB
	RAMBO – EzTz HW
	Auto Leveling

Mechanical
	Frame
	X-Axis
	Y-Axis
	Z-Axis
	Extruder
	Drive System
	Enclosure
	New Spool loc/feed
	Motor Selection
	Nozzle Sel/ Design
	Heat bed
	- PET tape?
	- Holding the bed?
	Auto Bed Leveling
	Build Prototypes

Electronics/ Electrical
	Wiring (HW vsConn)
	Power Supply
	Lights/LEDs
	Grd/ EMI Shielding
	Camera
	LCD
	SD or USB
	Switches
	Breadboard Testing

Testing
	Functional
	Speed
	Mechanical Performance
	Useability
	Environmental
	Op-Shock
	Non-Opshock
	EMC

Packaging/ Documentation
	Shipping Foam
	Unbox Manual
	Operation Manual
	Print Profiles
	BOM Creation

Manufacturing
	Assembly OHAI Kits
	Assembly lines (Separate vs. Common)
	-
	-
	PreSubs
	-
	-
	OpenERP Routing

	Resource Plan