## Sheet1
	EasyTAZ Mini – Product Development Cycle
	03-24	03-31	04-07	04-14	04-21	04-28	05-05	05-12	05-19	05-26	06-02	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22
Wdays to Launch	119 days left			104				84			69			54				34			19		10		0
	EVT - Engineering Validation Test / –- Azalea –-					DVT - Design Verification Test / –- Begonia –-					DMT/SAT–Des Maturity/Ship Apprv Test / –- Camellia –-					Production
	Design Validation – Functionally focused					Verification – Reliability focused – RBF cycles					Qual – MFG/ Quality/ Shippability
		(5 machines)					6/16	Build 15 machines/ DVT code release					8/04	Build 30 machines/ SAT code release					9/15
						Build 200
	3/24	Frame Design Decision: Cube or Mini_TAZ?					5/12	EVT Testing commences					6/30	Review & Risk SAT Entry approval, allow ordering parts for 30 SAT mach's					8/11	Risk decision to place orders 200 prod units
						Design Config LOCKED					9/22
						nozzle, bed leveing,					Finalize Packaging					Ship
						heater, electronics,					1st pal
	3/24	Electronics Design Decision: Thumbs up to current plan					07-14					09-12
						Print plastics for 30					Ship
						5/19	Review & Risk DVT Entry approval: to order parts for 15 DVT machines					Approved
						07-21			08-11	Print plastic for 200
						Risk order long
						lead items

	Items to Validate:					# of machine					Items to Verify:					# machine		Items to Verify:				# of machine
	1)	Printability					5					1) Performance(speed,...)					15		1) Manufacturability				30
	2)	Repeatability					use above					2) Repeatability/Reliability					use above		2) Longterm Reliability				same
	3)	Userablity					use above					3) Userability					use above
	4)	Mechanical Spec					use above					4) Environmental					3
	5)	Electrical spec					use above					5) Op Shock/ Vibration					3
						6) Non-Opshock					use above
						7) EMC/FCC					3
	Type of Test					Type of Test					How long?		Type of Test				How long?
	1)	Can it print as well as Guava					1) Print-Visual/Time measure					1) Long term reliability				72	hr
	2)	Is bed leveling working					2) Short print/Cal, 24hr print					24	hr	2) Assembly test run
	3)	Frame Stiffness					3) Hot, Hot/wet, Cold					3	hr/ea
	4)	Basic Electronics Function					4) Bump test
	5)					5) Drop test
						6) Near/far field test & FCC
	Test Acceptance or Pass/Fail Criteria					Test Acceptance or Pass/Fail Criteria					Test Acceptance or Pass/Fail Criteria
	1)					1)					1) E.g, No Calibration drift, visual/
	2)					2)					Measurement, dimension accuracy,
	3)					3)					consistency, visual printing quality
	4)					4)
	5)					5)

	Rules:	- Design changes allowed - No architect-related changes after					- Minor changes/improvements from RBF					- MFG/ “Ship” config hence NO change
		config “locked” date unless program risk (schedule, cost, …) studied					cycles allowed, no design config/architect-					unless last minute discovery renders
		& approved by the Project Approval Committee (PAC-stakeholders)					related changes unless approved by PAC					machine not shippable, req PAC apprv.

	PAC		Seth:
	Signed Off		Steven:
			Chris:
			Jeff:
	EasyTAZ Mini – Product Development Cycle_ Software & Firmware Functions & Features
	03-24	03-31	04-07	04-14	04-21	04-28	05-05	05-12	05-19	05-26	06-02	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	>>>
	119 days left			104				84			69			54				34			19		10		0
	EVT - Engineering Validation Test / –- Azalea –-					DVT - Design Verification Test / –- Begonia –-					DMT/SAT–Des Maturity/Ship Apprv Test / –- Camellia –-					Production
	Design Validation – Functionally focused					Verification – Reliability focused – RBF cycles					Qual – MFG/ Quality/ Shippability
		(5 machines)					6/16	Build 15 machines/ DVT code release					8/04	Build 30 machines/ SAT code release					9/15
						Build 200
	3/24	Frame Design Decision: Cube or Mini_TAZ?					5/12	EVT Testing commences					6/30	Review & Risk SAT Entry approval, allow ordering parts for 30 SAT mach's					8/11	Risk decision to place orders 200 prod units
						Design Config LOCKED					9/22
						nozzle, bed leveing,					Finalize Packaging					Ship
						heater, electronics,					1st pal
	3/24	Electronics Design Decision: Thumbs up to current plan					07-14					09-12
						Print plastics for 30					Ship
						5/19	Review & Risk DVT Entry approval: to order parts for >10 DVT machines					Approved
						07-21			08-11	Print plastic parts
						Risk order long
						lead items

			Software-Firmware Functions/ Features Requirements					SW-FW Functions/Features Requirement					SW-FW Functions/Features Reqmts

			- Auto bed leveling firmware					- Print from USB drive					- Help
			- Basic touch screen control of printer					- Auto bed calibration software					- Easy Print controls
			-					- Connect to printer from computer					- Wifi setup
			-					-					- Camera/light controls if they are incorporated
			-					-					- Sound
			-					-					- Video
			-					-					-
			-					-					-

	Rules	No restriction on code rolls					- Code roll as needed for performance improve					- Code locked down.
						or to support hardware fixes but not major					Changes only if it is a must to make
						architect changes that impact schedule					machine shippable