Lulzbot Mini/ Daffodil Ship Approval Review - 12/30/2014

Attendees: Jeff, Steven, Seth, Chris

Subject: Production and Ship approval

Goals: Determine what remained to be done and when so that production of shippable machine can
        commence and when.

Discussions/ Action Plan/ Checkpoints & Targets:

Agreed on 2 key checkpoints and associated actions & targets
Checkpoint 1: Monday 1/05 – manufacturing can commence production of shippable machines, with boxes left open awaiting items in Checkpoint 2.
Actions to complete to enter Checkpoint 1:
- New burn-in code to exercise Z-movement near the top to mitigate binding (Seth)
- Test and approve 1.1b RAMBO (Seth)
Checkpoint 2: Tues 1/6 or Weds 1/7 – manufacturing can produce machines and complete boxing and labeling “ready” for shipping. Not yet ship approved unless EMC testing completed and passed.
Actions to complete to enter Checkpoint 2:
- USB issue(s) resolved, proven and verified (Steven)
- Documentation editing and printing completed/ 50 sets ready (Steven)
- 2 mm wrench available (Seth/ Toni) – Completed / they are here!
- CURA “final/ ship-released” version ready for testing Monday AM 1/05 (Steven) and verified by R&D Monday EOD (Seth). This version will have improvements/fixes implemented but fix for checksum/ serial issue will NOT be rolled in at this time.

EMC testing & timing related to Ship Approval
1. Ship approval requires passing FCC and CE – here I am not sure we've finalized it, we need clarification whether we would ship anyway if for some crazy reason we fail the final official EMC test(s), either one or both tests (FCC, CE)?
2. Domestic ship approved once all EMC tests pass – Do we ship domestically first if we pass FCC but fail CE?
3. UK shipment can wait until CE doc write-up is done but must be before 1/10 to make the 1/22 shipment date.
Actions:
- ASAP schedule all EMC testing, preferably completion by Monday 5th /Tuesday 6thor sooner. Consider other testing centers in the state if need be (Seth/ Chris W.)
- CE testing and Certification Doc write-up done before 1/10 (Seth/ Chris W.)

Manufacturing Actions:
1. Continue assembling Daffodils up to electrical final assembly this week. (Chris)
2. Complete Elec final assembly/QC-Burn-in/Octopus on Monday 1/05 assuming 1.1b RAMBO checked out ok. (Chris)
3. Final box & label Tues or Weds assuming final documentation is available. (Chris)