EL-MS0096
Cartridge Fuses 125V 7A 5X20 MA UL LBC
Mouser / Digi-Key
576-0233007.MXP
BAM CONFIRMED MS0247 is correct fuse.
Is this a part of pomfret? (do we send a new cord with replacement PSU's?
Delivery 2-3 wks lead time if not ocean, approx 6/6/16
We have 68 in house already
We have 86 in house already
Need 525' (ordered 2 x 500' reels) Ships approx 5/23
42' needed, 152,000' on hand will not order for this build. George checking on correct on BOMs
Delivery 2-3 wks lead time if not ocean, approx 6/6/16
waiting for decision cyclops/allied Toni?
PO13242
Length updated 5.9.16 -bam
Length updated 5.9.16 -bam
Length updated 5.9.16 -bam
TTI stock avail 6/20/16
subcomponent of EL-HR0051
28B0672-000
subcomponent of EL-HR0051
MTR-M3100321
MTR-M3100321
Fastenal
long lead time, 10,000 reel
Mcmaster
95495K24
91120A120
Mcmaster
Mcmaster
8876T37
Mcmaster
91294A186
Fastenal
11225-04229
Mcmaster
9307K16
3-350820-2
3-350820-2
TTI stock avail 6/20/16 received 35,000 for Olive
Ordered from Allied Electronics KG
long lead time, 5,000 reel
Fastenal
11225-04229
Is this a part of pomfret? (do we send a new cord with replacement PSU's?)
Ordered from Allied Electronics will deliver 5/27/16 KG
6,345 on hand Is this a part of pomfret? (do we send a new cord with replacement PSU's?)
AMP
2200 pc min/mult
was on TAZ5 and pomfret
BAM CONFIRMED MS0347 is correct fuse.
PO13424
6,345 on hand KG Is this a part of pomfret? (do we send a new cord with replacement PSU's?)
Heilind
10,600 on hand qty
## Sheet1
Category	AO Part #	Description	Manufacturer	Manufacturer PN	Distributor	Distributor SKU	Qty Per	UOM	Price Per Unit	Price Total	Qty to Order	PO	Date	ETA	NOTES
										$114.91	160
	Kim	edited by bam 5.5.16
	Toni	Bold indicates that parts are subcomponents of EL-HR0051

Electronic	EL-CA0030	6ft 18AWG Power Cord Cable w/ 3 Conductor PC Power Connector Socket (C13/5-15P) – Black			Linvox		1	ea	$1.10	$1.10	160				4,750 on hand KG Is this a part of pomfret? (do we send a new cord with replacement PSU's?)
Electronic	EL-MS0143	Conn Fast Receptacle14-16 AWG .250 (2200 Unit Reel)	TTI	3-350819-2	TTI	3-350819-2	7	ea	$0.069	$0.48	1120				15,400 pc on hand KG 2200 pc min/mult
Electronic	PP-MP0028	AC Power Entry Modules SC MT FUSED .25" TAB	Bulgin	161-PF0030/63	Allied	161-PF0030/63	1	ea	$2.86	$2.86	160	PO13370	05/06/16	05/20/16	15,400 pc on hand Ordered from Allied Electronics will deliver 5/27/16 KG
Electronic	EL-MS0347	FUSE CERAMIC 6.3A 250VAC 5X20MM	Littlefuse	023406.3MXP	Mouser & TTI	023406.3MXP	2	ea	$0.37	$0.74	320	PO14865	07/29/16	08/03/16	7/29/16 purchased 510 from Mouser for fill-in last stock available leadtime 10 wks. KG BAM CONFIRMED MS0347 is correct fuse.
Electronic	EL-MS0248	CONN RING 14-16 AWG #10 PIDG	TE	2-36160-1	Digikey / TTI	A1072TR-ND	7	ea	$0.096	$0.67	1120				35,000 on hand TTI stock avail 6/20/16 received 35,000 for Olive
Electronic	EL-PS0031	Mean Well Switching Power Supplies 504W 24V 21A Power Supply W/PFC	Mean Well	RSP-500-24	Sager	709-RSP500-24	1	ea	$71.00	$71.00	160			see note	Scheduled delivery Sager
Electronic	EL-WR0106	16AWG Stranded – Red		C2065A.21.03	Allcable	HU15691626RD	0	mm	$0.000	0	0				Not in this part
Electronic	EL-WR0121	16AWG Stranded – Black		HU15691626BK	Allcable	HU15691626BK	180	mm	$0.000	$0.05	28800				95 feet Length updated 5.9.16 -bam
Electronic	EL-WR0124	16AWG Stranded – Green w/ yellow stripe		HU15691626GN	Allcable	HU15691626GN	120	mm	$0.000	$0.03	19200				63 feet Length updated 5.9.16 -bam
Electronic	EL-WR0123	16AWG Stranded – White		HU15691626WE	Allcable	HU15691626WE	180	mm	$0.000	$0.05	28800				95 feet Length updated 5.9.16 -bam
Electronic	EL-MS0246	Conn Ring 16-22 AWG #4 Red PIDG	TTI	3-323758-1	Digikey	A27229CT	2	ea	$0.443	$0.89	320				25,000 on hand long lead time, 5,000 reel
Electronic	EL-CA0073	Multi-Conductor Cables 14AWG 4C UNSHLD, BLACK	Belden Wire & Cable	1310A 010U500	Mouser	566-1310A-U500-10	1050	mm	$0.00	$4.61	168000	PO13424	05/06/16	05/25/16	Need 525' (ordered 2 x 500' reels) Ships approx 5/23, subcomponent of EL-HR0051
Electronic	TL-CS0136	Flame-Retardant Heat-Shrink Tubing, 0.21" ID Before Shrinking, 25' Long			Mcmaster	7864K32	80	mm	$0.00	$0.12	12800		see note	see note	42' needed, 152,000' on hand will not order for this build. George checking on correct on BOMs, subcomponent of EL-HR0051
Electronic	EL-MS0249	Front Mount Male, 4 pin, solder			WEIPU	SP2112/P41N	0	ea	$1.87	$0.00	0	PO13404	05/06/16	06/06/16	Delivery 2-3 wks lead time if not ocean, approx 6/6/16 – This is used on the TAZ control box side of things, not in Pomfret
Electronic	EL-MS0250	Cable connector female, 4 pin, solder			WEIPU	SP2110/S4II1N	1	ea	$1.87	$1.87	160	PO13404	05/06/16	06/06/16	Delivery 2-3 wks lead time if not ocean, approx 6/6/16, subcomponent of EL-HR0051
Electronic	EL-SW0023	SWITCH ROCKER DPST 20A 250V, illuminated red			Digikey/Heilind	EG1535-ND	1	ea	$1.496	$1.50	160			see note	13,950 on hand
Hardware	HD-MS0290	Mil. Spec. Grommet, Fits 9/16" Diameter Hole & 1/16" Thick Panel, MS-35489-9	Mcmaster	9307K16	Fastenal	11225-04229	1	ea	0.12	$0.12	160				purchased from Fastenal, not in bin program
Hardware	HD-BT0155	Black Alloy Steel Flat-Head Socket Cap Screw, Class 10.9, M4 Size, 6mm Length, .70mm Pitch	Mcmaster	91294A186	Fastenal	40931	4	ea	0.01	$0.04	640				Bin hardware item
Hardware	HD-MS0289	Nylon Loop Clamp, 5/16" ID, Black	Mcmaster	8876T37	Fastenal	708911	1	ea	0.0298	$0.03	160				was on TAZ5 and pomfret
Hardware	HD-WA0035	Metric 18-8 Stainless Steel External Serrated Lock Washer, M3 Screw Size, 6mm OD, 0.4mm min Thick	Mcmaster	91120A120	Fastenal	11511313	1	ea	$0.018	$0.02	160				Bin hardware item
Hardware	HD-MS0288	Adhesive-Back Bumper, Tapered, Polyurethane, 1/2" Wide, 15/64" High, Black	Mcmaster	95495K24	Fastenal	503049	4	ea	$0.117	$0.47	640	PO14829	07/27/16	07/28/16	was on TAZ5 and pomfret pkg = 50 $5.85ea 0.117ea
Hardware	HD-BT0128	M3 x 6 Bolt, FHCS Black-Oxide	Mcmaster	91294A126	Fastenal	40921	10	ea	$0.040	$0.40	1600				Bin hardware item
Hardware	HD-NT0001	M3 Nyloc Nut, Zinc Plated	Mcmaster	90576A102	Fastenal	40143	2	ea	$0.01	$0.02	320				Bin hardware item
Hardware	HD-WA0001	M3 Washer, Steel, Zinc Plated	Mcmaster	40352	Fastenal	40352	2	ea	$0.00	$0.00	320				Bin hardware item
Mechanical	PP-MP0096 – PP-MP0104	Upper PS case, RSP			Star Precision		1	ea	$8.510	$8.51	160	PO13523	05/16/16	05/31/16	We have 68 in house already, make sure it's the most recent rev
Mechanical	PP-MP0097 – PP-MP0103	Lower PS case, RSP			Star Precision		1	ea	$18.660	$18.66	160	PO13523	05/16/16	05/31/16	We have 86 in house already, make sure it's the most recent revision
Electronic	EL-MS0254	FERRITE BRDBAND CYLINDER 17.07MM – 28B0672-000	Laird	28B0672-000	Digikey	240-2769-ND	1	ea	0.385	$0.39	160				12 wk lead time, digikey stock subcomponent of EL-HR0051
Electronic	EL-MS0259	HEATSHRNK DL WL Q53X 3/4"X4'BLK	EDC	67-30751	Digikey	Q53X034B-ND	0.0666666667	ea	4.116	$0.27	10.6666666667	PO14634	07/14/16	08/11/16	$80 / 100 ft subcomponent of EL-HR0051

		Solder
		Laser etching

		Allcable – Cable Assembly delivery dates Please see following schedule:				Don't order yet
						Items that can be ordered
						We have enough/on order

		Description	End	Wire	Color	Length	End
		Ground wire from Inlet to Stud	EL-MS0143	EL-WR0124	Green w/ Yellow	60mm	EL-MS0246
		Ground wire from Stud to PS	EL-MS0246	EL-WR0124	Green w/ Yellow	60mm	EL-MS0248
		Neutral line from Inlet to Switch	EL-MS0143	EL-WR0121	Black	70mm	EL-MS0143
		Neutral line from Switch to PS	EL-MS0143	EL-WR0121	Black	100mm	EL-MS0248
		Live line from Inlet to Switch	EL-MS0143	EL-WR0123	White	70mm	EL-MS0143
		Live line from Switch to PS	EL-MS0143	EL-WR0123	White	110mm	EL-MS0248