TL-CS0116
Saunders UHU Glue Stick, 0.74 oz., White
Amazon
PO13371
0.75 kg = 50 extruders
provided The print shop revised ART, quote $140 / 2,000 cards.
confirmed delivery 5/5/16
confirmed delivery 5/5/16
PO for all Extruders
329'
BAM wants Elmers glue sticks TL-CS0117
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
PO for all Extruders
Received 3 rolls, 7 shipping 5/23 329'
received nozzels for 0.50 mm, waiting on delivery of 0.60
Confirmed 4/29 delivery
Ordered 850 pc, 400 in stock to ship now, balance 4-6 wks per Toni
300' Backorder due 4/20 ship from Mouser
(need 10 reels 0.75ea) 0.75 kg = 50 extruders
## Sheet1
AO-Hex Printhead v0.1

part	qty	Notes	AO Part No	Cost per	Cost total
Hextruder Block (body)	1	new		$4.01	$4.01
Herringbone small gear	1	Red		$0.34	$0.34
Herringbone large gear	1	Red		$2.34	$2.34
Reloaded bearing washer	1		PP-GP0060	$0.02	$0.02
Hobbed Bolt M8x50 26mm offset	1		HD-BT0108	$5.50	$5.50
Extruder latch	1	Red		$0.26	$0.26
Extruder idler block	1		PP-GP0059	$0.90	$0.90
Motor wires -2	1		EL-HR0016-2	$13.72	$13.72
8mm smooth rod x 18-19mm, Stainless Steel	1		HD-RD0004	$4.73	$4.73
608 Bearing	3	needs to be sealed type	HD-MS0013	$0.45	$1.35
Extruder comp spring – music wire	2		HD-MS0027	$0.22	$0.44
M3 set screw	1		HD-BT0012	$0.02	$0.02
M3x12mm SCHS	4		HD-BT0039	$0.01	$0.05
M3x25 SCHS	1		HD-BT0041	$0.03	$0.03
M3 washer	5		HD-WA0001	$0.00	$0.01
M3 Nut	2		HD-NT0004	$0.01	$0.02
M4x55 SCHS	2		HD-BT0052	$0.08	$0.16
Black plastic thumbscrew for M4	2		HD-MS0031	$0.10	$0.19
M4 Nut, Zinc Plated Steel	2		HD-NT0011	$0.00	$0.01
M4 Washer	4		HD-WA0005	$0.00	$0.01
M8 Nyloc Nut	1		HD-NT0002	$0.05	$0.05
M8 Washer, zinc plated steel	3		HD-WA0006	$0.01	$0.04
M8 Shim Washer, 0.5mm	1		HD-WA0008	$0.05	$0.05
M8 Shim Washer, 1.0mm	1		HD-WA0009	$0.06	$0.06
Hextruder Mount, TAZ	1	new		$6.50	$6.50
Brass M3 heatset inserts	4		HD-MS0030	$0.07	$0.29
M4 Nut, Zinc Plated Steel	2		HD-NT0011	$0.00	$0.01
M4 washer	2		HD-WA0005	$0.00	$0.01
M4x20 SCHS	2		HD-BT0010	$0.04	$0.07
Label, Extruder E-step Number	1		DC-LB0017	$1.00	$1.00
Extruder Fan Mount v1.0, TAZ	1		PP-GP0153	$1.12	$1.12
Brass M3 heatset inserts	4		HD-MS0030	$0.07	$0.29
12 or 24V DC fan, 40x40x10	1		2 PN's	$2.50	$2.50
Male pin, 24-30AWG tin crimp	2		EL-MS0058	$0.00	$0.00
Male 2 pin connector housing	1		PP-MP0059	$0.00	$0.00
M3 washer	2		HD-WA0001	$0.00	$0.00
M3x12mm SCHS	6		HD-BT0039	$0.01	$0.07
AO-Hex hotend kit	1			$24.00	$24.00
micro blower	1			$8.00	$8.00
M2 heatset insert	1		PP-MP0066	$0.09	$0.09
M2x6 SCHS	1			$0.05	$0.05

Shipping Materials

Harness
24AWG Stranded – Red	1000	mm	EL-WR0103	$0.00	$0.26			Digikey	C2015R-1000-ND
24AWG Stranded – Black	1000	mm	EL-WR0105	$0.00	$0.26			Digikey	C2015B-1000-ND
	1		EL-MS0131	$2.51	$2.51			Digikey	A1358-ND
20-24 AWG Tin Pin for Plug	2		EL-MS0123	$0.22	$0.45			Digikey	A31991TR-ND
Cable Clamp for 14-Pos; 0.453” opening	1		EL-MS0129	$2.55	$2.55			Digikey	A32516-ND
CONN TERM FEMALE 22-24AWG TIN	2		EL-MS0059	$0.05	$0.10			Digikey	WM2510-ND	Molex Inc.	16-02-0102
CONN HOUSING 2POS .100 W/LATCH	1		PC-CN0001	$0.13	$0.13			Digikey	WM2900-ND
Tubing, Corrugated Loom .25"	960	mm (red?)	EL-MS0073	$0.00	$0.92			McMaster-Carr Supply Company	7840K31	Panduit	CLT25F-C20

				Cost per kit	$85.47
				DOES NOT INCLUDE SHIPPING MATERIALS YET

## BOM
Kanyu BOM
Category	AO Part #	Description	Manufacturer	Manufacturer PN	Distributor	Distributor SKU	Qty Per	UOM	Price Per Unit	Price Total	Qty to Order	PO	PO Date	Expected Date	Notes	Alternates
					500
Printed Part	PP-GP0200	flexystruder body 2.0, for hexagon, lulzbot green			Aleph Objects Inc.		1	ea	$4.01	$4.01	500
Printed Part	PP-GP0061	herringbone_large_gear, Black			Aleph Objects Inc.		1	ea	$0.34	$0.34	500
Printed Part	PP-GP0062	herringbone_small_gear, Black			Aleph Objects Inc.		1	ea	$2.34	$2.34	500
Printed Part	PP-GP0060	Wade Reloaded Bearing Washer			Aleph Objects Inc.		1	ea	$0.02	$0.02	500
Printed Part	PP-GP0202	Extruder Mount for Hex v1.0, TAZ, lulzbot green			Aleph Objects Inc.		1	ea	$2.88	$2.88	500				price form ERP for standard extruder mount
Printed Part	PP-GP0153	Extruder Fan Mount v1.0, TAZ			Aleph Objects Inc.		1	ea	$1.12	$1.12	500

Electronic	EL-MS0251	CONN HOUSING 16POS .100 DUAL	Molex		TTI	WM2525-ND	1	ea	$0.526	$0.53	500	PO12924	04/11/16	04/20/16
Electronic	EL-MS0205	CONN TERM MALE 22-24AWG TIN	Molex		TTI	WM2517TR-ND	9	ea	$0.13	$1.17	4500	PO12924	04/11/16	04/20/16
Electronic	EL-MS0212	CONN PIN 24-30AWG CRIMP TIN	Molex	16-02-0108	TTI	MOL16-02-0108	4	ea	$0.081	$0.32	2000			see note	on hand 20k reel just purchased.
Electronic	EL-WR0127	Hook-up Wire 26AWG SOLID PTFE, WHT	Mouser	602-2843/1-100-01	Mouser	602-2843/1-100-01	150	mm	$0.000	$0.04	75000	PO12882	04/07/16	04/21/16	Received

Electronic	EL-FA0011	FAN,24VDC,Sleeve,5.75CFM,40X40X10MM,60mA 6000RPM,1.44W,280MM LEADS,CE/RoHS			Kysan	TF4010-24H-S	1	ea	$1.45	$1.45	500	PO13074	04/16/16	04/22/16	Received 400 Ordered 850 pc, 400 in stock to ship now, balance 4-6 wks per Toni

Mechanical	HD-BT0108	Hobbed Bolt M8x50 26mm offset			Quatro		1	ea	$4.99	$4.99	500	PO12884	04/06/15	04/27/16	Received Confirmed 4/29 delivery

Electronic	TL-CS0083	EMI/RFI-Shield Heat-Shrink Tubing 3/16" ID Before, 3/32" ID After, 48" L, Black			Allcable	7937K31	0	mm	$0.01	0	0
Electronic	TL-CS0129	Interference-Shielding Heat-Shrink Tubing, 3/8" ID Before, 3/16" ID After, 48" Long, Black			Allcable	7937K33	0	mm	$0.03	0	0				replaced with EL-MS0247 on olive and longfin

Electronic	EL-MS0247	Heat Shrink Tubing - 0.19-0.09 - Black, 100'					80	mm	$0.02	$1.45
Electronic	EL-FA0020	RFB2008 Micro Blower, 30 AWG wire 250mm long			Pelonis		1	ea	$6.54	$6.54	500	PO13035	04/14/16	05/04/16	In stock do not need to order. TS 2k on hand

Hardware	HE-SH0041	Hexagon Hotend, Lulzbot Edition, 3.0mm Filament, 0.6mm nozzle			Reprapdiscount	HE-SH0041	1	ea	$23.00	$23.00	500	PO12909	04/07/16	05/04/16	received nozzles for 0.50 mm, waiting on delivery of 0.60

Electronic	EL-MT0001	NEMA 17 Stepper Motors			Changzhou FTX	SY42STH47-1504A	1	ea	$7.50	$7.50	500			see notes	10 K on hand

Hardware	HD-BT0012	M3 set screw			Fastenal		1	ea	$0.02	$0.02	500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-BT0104	M3 x 8 Bolt, BHCS, SST			Fastenal	92095A181	2	ea	$0.088	$0.18	1000	PO12837	04/05/16	04/12/16	Received
Hardware	HD-BT0039	M3 x 12 Bolt, SHCS Black-Oxide			Fastenal		9	ea	$0.02	$0.14	4500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-WA0001	M3 Washer, Steel, Zinc Plated			Fastenal		5	ea	$0.02	$0.08	2500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-NT0004	M3 Nut, Zinc Plated			Fastenal		1	ea	$0.01	$0.01	500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-NT0011	M4 Nut,Zinc-Plated Steel			Fastenal		2	ea	$0.00	$0.01	1000	PO12837	04/05/16	04/12/16	Received
Hardware	HD-WA0005	M4 Washer			Fastenal		2	ea	$0.00	$0.01	1000	PO12837	04/05/16	04/12/16	Received
Hardware	HD-NT0002	M8 Nyloc Nut, Zinc Plated			Fastenal		1	ea	$0.03	$0.03	500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-WA0006	M8 Washer, Steel, Zinc Plated			Fastenal		3	ea	$0.02	$0.05	1500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-WA0008	Metric Spring Steel Shim - DIN 988 0.5mm Thick, 8mm ID, 14mm OD			Fastenal		1	ea	$0.05	$0.05	500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-WA0009	Metric Spring Steel Shim - DIN 988 1.0mm Thick, 8mm ID, 14mm OD			Fastenal		1	ea	$0.06	$0.06	500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-MS0030	M3-.5 3.8mm Heatset Insert			Fastenal		6	ea	$0.04	$0.22	3000	PO12837	04/05/16	04/12/16	Received
Hardware	HD-BT0010	M4 x 20 Bolt, SHCS Black-Oxide			Fastenal		2	ea	$0.14	$0.28	1000	PO12837	04/05/16	04/12/16	Received
Hardware	PP-MP0066	Metric Brass Heat-Set Insert for Plastics, Tapered, M2-.4 Internal Thread, 2.9MM Length			CEH		1	ea	$0.09	$0.09	500	PO12572	03/17/16	04/14/16	RECEIVED 4-6 week lead time on these
Hardware	HD-MS0230	M2 x 6 SHCS, Black-Oxide			Fastenal		1	ea	$0.00	$0.00	500	PO12837	04/05/16	04/12/16	Received
Hardware	HD-MS0058	Wire Tie, 8"		63126	Electronics Distributors Corporation		1	ea	$0.022	$0.02	500			see note	286000 on hand do not need to order
Consumable	TL-CS0117	Elmer's Glue Sticks, .77oz			Dick Blick Art Materials	23810-1020	1	ea	$1.30	$1.30	500	PO13371	05/04/16	05/13/16	Received BAM wants Elmers glue sticks TL-CS0117
Consumable	TL-CS0040	Extreme-Temperature Pipe Sealant & Threadlocker, 4 oz bottle, blue			Mcmaster	7604A55	0.5	g	$0.066	$0.03	250			see note	Bob will let us know when to order
Hardware	HD-TB0006	PTFE tube, 1/4” OD x 1/8” ID, for fabrication			Mcmaster	8547K23	50	mm	$0.01	$0.53	25000	PO13020	04/13/16	04/19/16	received

Electronic	EL-MS0246	CONN RING 16-22 AWG #4 Red PIDG – Reel 5000		2-323758-1	Digikey / TTI	A107160CT-NDA27229TR-ND	1	ea	$0.43	$0.43	500	PO11489		see note	Have overage from olive purchase 10k , 12 wk leadtime for full reel 5000 pc	01/28/16	Have overage from olive purchase 10k , 12 wk leadtime for full reel 5000 pc
Electronic	EL-WR0040	Wire - Single Conductor 20AWG SOLID PTFE, RED			Mouser	602-2856/1-100-03	200	mm	$0.00	$0.78	100000	PO12926	04/08/16	05/23/16	Received 3 rolls, 5 shipping 5/23 329'
Hardware	HD-WA0035	Metric 18-8 Stainless Steel External Serrated Lock Washer, M3 Screw Size, 6mm OD, 0.4mm min Thick		11511313	Fastenal	91120A120	1	ea	$0.020	$0.02	500	PO12837	04/05/16	04/12/16	Received

Mechanical	HD-MS0282	608-2RS ABEC3/C3 Rubber Sealed Bearing – BLACK			JSB	608-2RS ABEC3/C3	2	ea	$0.42	$0.84	1000	PO12911	04/08/16	04/19/16	received
					0
Shipping	SH-PG0059	Mailers, Indestructo, 7 x 5 x 4			Uline	S-971	1	ea	$0.76	$0.76	500	PO11415	03/18/16	03/24/16	Received 500 pcs
Shipping	SH-PA0019	Bubble 1/8x48x750 perf 12" slit 2-24" rolls			Shipper Supply		1	sheet	$0.15	$0.15	500	PO12807	04/01/16	04/13/16	Stock ordered will cover this BOM
Shipping	SH-PG0002	3 x 4" 2 Mil Reclosable Polypropylene Bags			Uline	S-1296	1	ea	$0.03	$0.03	500	PO13147	04/28/16	05/09/16	received
	SH-PA0039	Roll of 48"x1/4" Thick Foam, Split at 12" - 225 feet Per Roll			Shipper Supply		0.0011111111111	ea			1	PO12807	04/13/16	04/19/16	Stock ordered will cover this BOM
Label	DC-LB0068	Label, LulzBot TAZ Flexystruder Tool Head v2c, 0.6 Nozzle, Front			Sticker Giant		1	ea	$0.23	$0.23	500	PO13233	04/28/16	05/05/16	Received confirmed delivery 5/5/16
Label	DC-LB0069	Label, LulzBot TAZ Flexystruder Tool Head v2c, 0.6 Nozzle, Back			Sticker Giant		1	ea	$0.23	$0.23	500	PO13233	04/28/16	05/05/16	Received confirmed delivery 5/5/16
Sample	RM-TE0027	LulzBot Green NinjaFlex TPE Filament, 3mm. 0.75kg			Fenner Drives		0.02	ea	$34.41	$0.69	10	PO13450	05/10/16	05/31/16	Confirmed, will ship 5/13 KG(need 10 reels 0.75ea) 0.75 kg = 50 extruders
Label	DC-LB0082	LulzBot TAZ Flexystruder v2 Serial Number Label					1	ea			500				5/9/16 Confirmed serial number labels are on hand.
Documentation	DC-MS0047	v2 Tool Head Instruction Card			The print shop of Loveland		1	ea	$0.070	$0.07	500	PO13426	05/06/16	05/11/16	Received
Documentation	DC-MS0054	Firmware Update Warning Cards					1	ea	1.000	$0.08	500	PO12853	04/05/16	04/08/16	Received 2,000
Label	DC-LB0104	Tool Head Wiring Connector Alignment Label			Sticker Giant		1	ea	$0.03	$0.03	500				have enough for current build
					$65.02
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0
					0

## DO NOT USE Draft Sub-assemblies
Category	AO Part #	Description			Manufacturer		Qty Per	UOM	Price Per Unit	Price Total

		Flexystruder V2 body w/ PTFE
Printed Part	PP-GP0200	flexystruder body 2.0, for hexagon, lulzbot green			Aleph Objects Inc.		1	ea	$4.01	$4.01
Hardware	HD-TB0006	PTFE tube, 1/4” OD x 1/8” ID, for fabrication			Mcmaster		50	mm	$0.01	$0.53

		Herringbone large gear sub-assembly, black
Printed Part	PP-GP0061	herringbone_large_gear, Black			Aleph Objects Inc.		1	ea	$0.34	$0.34
Mechanical	HD-BT0108	Hobbed Bolt M8x50 26mm offset			Quatro		1	ea	$4.99	$4.99

		Herringbone small gear sub-assembly, black
Printed Part	PP-GP0062	herringbone_small_gear, Black			Aleph Objects Inc.		1	ea	$2.34	$2.34
Hardware	HD-BT0012	M3 set screw			Fastenal		1	ea	$0.02	$0.02
Hardware	HD-NT0004	M3 Nut, Zinc Plated			Fastenal		1	ea	$0.01	$0.01

		Flexystruder V2 extruder body sub-assembly
		Flexystruder V2 body w/ PTFE
		Herringbone large gear sub-assembly, black
Printed Part	PP-GP0060	Wade Reloaded Bearing Washer			Aleph Objects Inc.		1	ea	$0.02	$0.02
Mechanical	HD-MS0282	608-2RS ABEC3/C3 Rubber Sealed Bearing – BLACK			JSB		2	ea	$0.42	$0.84
Hardware	HD-NT0002	M8 Nyloc Nut, Zinc Plated			Fastenal		1	ea	$0.03	$0.03
Hardware	HD-WA0006	M8 Washer, Steel, Zinc Plated			Fastenal		3	ea	$0.02	$0.05
Hardware	HD-WA0008	Metric Spring Steel Shim - DIN 988 0.5mm Thick, 8mm ID, 14mm OD			Fastenal		1	ea	$0.05	$0.05
Hardware	HD-WA0009	Metric Spring Steel Shim - DIN 988 1.0mm Thick, 8mm ID, 14mm OD			Fastenal		1	ea	$0.06	$0.06
Hardware	HD-NT0011	M4 Nut,Zinc-Plated Steel			Fastenal		2	ea	$0.00	$0.01

		NEMA 17 sub-assembly, extruder
Electronic	EL-MT0001	NEMA 17 Stepper Motors			Changzhou FTX	SY42STH47-1504A	1	ea	$7.50	$7.50
Electronic	EL-MS0247	Heat Shrink Tubing – 0.19-0.09 – Black, 100'			Electronics Distributor Corp	88-01870	100	mm	$0.00	$0.07	This is the replacement heat shrink
Electronic	TL-CS0083	EMI/RFI-Shield Heat-Shrink Tubing 3/16" ID Before, 3/32" ID After, 48" L, Black			Allcable	7937K31	45	mm	$0.01	$0.66	These were dropped in favor of unshielded heatshrink 3/29/16, EL-MS0247
Electronic	TL-CS0129	Interference-Shielding Heat-Shrink Tubing, 3/8" ID Before, 3/16" ID After, 48" Long, Black			Allcable	7937K33	35	mm	$0.03	$0.93	These were dropped in favor of unshielded heatshrink 3/29/16, EL-MS0247
Electronic	EL-MS0212	CONN PIN 24-30AWG CRIMP TIN	Molex	16-02-0108	TTI	MOL16-02-0108	4	ea	$0.081	$0.32

		TAZ Toolhead V2, print fan sub-assembly
Printed Part	PP-GP0153	Extruder Fan Mount v1.0, TAZ			Aleph Objects Inc.		1	ea	$1.12	$1.12
Electronic	EL-FA0011	FAN,24VDC,Sleeve,5.75CFM,40X40X10MM,60mA 6000RPM,1.44W,280MM LEADS,CE/RoHS			Kysan	TF4010-24H-S	0	ea	$1.45	0
Electronic	EL-FA0032	Pelonis FAN 24V 40x40mm Low flow	Pelonis	C4010L24BPLB1-7	Pelonis	C4010L24BPLB1-7	1	ea	3.13	$3.13
Hardware	HD-MS0030	M3-.5 3.8mm Heatset Insert			CEH		4	ea	$0.04	$0.14
Hardware	HD-BT0039	M3 x 12 Bolt, SHCS Black-Oxide			Fastenal		4	ea	$0.02	$0.06
Electronic	EL-MS0205	CONN TERM MALE 22-24AWG TIN	Molex		Heilind	WM2517TR-ND	2	ea	$0.13	$0.26

		Hotend V2, 3.0mm filament, 0.6mm nozzle, sub-assembly
Hardware	HE-SH0041	Hexagon Hotend, Lulzbot Edition, 3.0mm Filament, 0.6mm nozzle			Reprapdiscount	HE-SH0041	1	ea	$23.00	$23.00
Electronic	EL-MS0205	CONN TERM MALE 22-24AWG TIN	Molex		Heilind	WM2517TR-ND	5	ea	$0.13	$0.65
Electronic	EL-MS0210	CONN RING UNINS 15-20AWG #M3		160344-2	Digikey	A107160CT-ND	1	ea	$0.09	$0.09
Electronic	EL-WR0040	Wire - Single Conductor 20AWG SOLID PTFE, RED			Mouser	602-2856/1-100-03	200	mm	$0.00	$0.78
Hardware	HD-WA0035	Metric 18-8 Stainless Steel External Serrated Lock Washer, M3 Screw Size, 6mm OD, 0.4mm min Thick		11511313	Fastenal	91120A120	1	ea	$0.020	$0.02
Consumable	TL-CS0040	Extreme-Temperature Pipe Sealant & Threadlocker, 4 oz bottle, blue			Mcmaster	7604A55	0.5	g	$0.066	$0.03

		Extruder V2 microblower sub-assembly
Electronic	EL-FA0020	RFB2008 Micro Blower, 30 AWG wire 250mm long			Pelonis		1	ea	$6.54	$6.54
Electronic	EL-MS0212	CONN PIN 24-30AWG CRIMP TIN	Molex	16-02-0105	TTI	MOL16-02-0108	2	ea	$0.036	$0.07

		TAZ Flexystruder V2 extruder mount sub-assembly
Printed Part	PP-GP0202	Extruder Mount for Hex v1.0, TAZ, lulzbot green			Aleph Objects Inc.		1	ea	$2.88	$2.88
Hardware	HD-MS0030	M3-.5 3.8mm Heatset Insert			Fastenal		2	ea	$0.04	$0.07
Hardware	PP-MP0066	Metric Brass Heat-Set Insert for Plastics, Tapered, M2-.4 Internal Thread, 2.9MM Length			Fastenal		1	ea	$0.09	$0.09

		TAZ Flexystruder V2 tool head final sub-assembly
		Flexystruder V2 extruder body sub-assembly
		Herringbone small gear sub-assembly, black
		NEMA 17 sub-assembly, extruder
		Toolhead V2, print fan sub-assembly
		Hotend V2, 3.0mm filament, 0.6mm nozzle, sub-assembly
		Extruder V2 microblower sub-assembly
		Flexystruder V2 extruder mount sub-assembly
Electronic	EL-MS0251	CONN HOUSING 16POS .100 DUAL	Molex		Heilind	WM2525-ND	1	ea	$0.526	$0.53
Hardware	HD-BT0039	M3 x 12 Bolt, SHCS Black-Oxide			Fastenal		5	ea	$0.02	$0.08
Hardware	HD-WA0001	M3 Washer, Steel, Zinc Plated			Fastenal		5	ea	$0.02	$0.08
Hardware	HD-WA0005	M4 Washer			Fastenal		2	ea	$0.00	$0.01
Hardware	HD-BT0010	M4 x 20 Bolt, SHCS Black-Oxide			Fastenal		2	ea	$0.14	$0.28
Hardware	HD-MS0230	M2 x 6 SHCS, Black-Oxide			Fastenal		1	ea	$0.00	$0.00
Shipping	HD-MS0348	ESD Foam 40mm x 20mm x 10mm - Extruder Pin Protector			Paqsource	015-29146	1	ea	$0.03	$0.03
Hardware	HD-MS0058	Wire Tie, 8"		63126	Electronics Distributors Corporation		1	ea	$0.022	$0.02
Label	DC-LB0082	LulzBot TAZ Flexystruder v2 Serial Number Label					1	ea

		Flexystruder V2 accessory kit
Shipping	SH-PG0002	3 x 4" 2 Mil Reclosable Polypropylene Bags			Uline	S-1296	1	ea	$0.04	$0.04
Consumable	TL-CS0117	Elmer's Glue Sticks, .77oz			Dick Blick Art Materials	23810-1020	1	ea	$1.30	$1.30
Sample	RM-TE0027	LulzBot Green NinjaFlex TPE Filament, 3mm. 0.75kg			Fenner Drives		0.02	ea	$34.41	$0.69

	KT-CP0090	TAZ LulzBot TAZ Flexystruder Tool Head V2
		Flexystruder V2 tool head final sub-assembly
Shipping	SH-PG0059	Mailers, Indestructo, 7 x 5 x 4			Uline	S-971	1	ea	$0.76	$0.76
Shipping	SH-PA0019	Bubble 1/8x48x750 perf 12" slit 2-24" rolls			Shipper Supply		1	sheet	$0.15	$0.15
	SH-PA0039	Roll of 48"x1/4" Thick Foam, Split at 12" - 225 feet Per Roll			Shipper Supply		0.0011111111111	ea
Label	DC-LB0068	Label, LulzBot TAZ Flexystruder Tool Head v2c, 0.6 Nozzle, Front			Sticker Giant		1	ea	$0.23	$0.23
Label	DC-LB0069	Label, LulzBot TAZ Flexystruder Tool Head v2c, 0.6 Nozzle, Back			Sticker Giant		1	ea	$0.23	$0.23
Documentation	DC-MS0047	v2 Tool Head Instruction Card					1	ea	$0.080	$0.08
		Flexystruder V2 accessory kit