## Sheet1
EasyTAZ Mini - Work Breakdown Schedule
	TASKS		OWNER	MAN Hrs	03-24	03-31	04-07	04-14	04-21	04-28	05-05	05-12	05-19	05-26	06-02	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08
					EVT					DVT					SAT					Production
Architect			Seth
	Cube or Lulzbot? Decision		Seth
	- CAD		Seth
	- Build mockups		Seth
	- Cost estimate		Seth/ Chris
	Electronics- Controller & Comm		TBD
	- Research features		Aaron
	- Research Market trends		Aaron
	- Pros & Cons on FW effort		Aaron
	- Final Config/feature proposal		Seth
	- Final Config Decision		All
	Non-UL/UL Ready/ Full UL?		Seth & All
	- Define what need to be done		Seth/ Chris
	- Re cost estimate		Seth
Software
	SW Feature List		Seth/ Aaron					<<<
	BBB – LCD touch		Aaron/Aeva
	BBB – WiFi		Aaron/Aeva
	BBB – Smart Phone		Aaron/Aeva
	BBB – USB		Aaron/Aeva
	BBB – Camera		Aaron/Aeva
	User Interf Menu Diagr/Coding		Aaron/Aeva
	Interface Controls (Touch Scrn)		Aaron/Aeva
	System Integration		Aaron/Aeva
Firmware
	RAMBO – SD		Aaron/Seth
	RAMBO – BBB		Aaron/Seth
	RAMBO – EZT HW		Aaron/Seth
	Auto Leveling		Aaron/Seth
Mechanical			Seth
	Frame		Seth
	X-Axis		Seth
	Y-Axis		Seth
	Z-Axis		Seth
	Extruder		Seth/ Brent
	Drive System		Seth
	New Spool loc/feed		Seth					<<<
	Motor Selection		Seth
	Nozzle Sel/ Design		Seth/ Brent					<<<
	Heat bed		Seth/ Brent					<<<
	- PET tape?
	- Holding the bed?
	Auto Bed Leveling		Seth/ Brent
Electronics/ Electrical			Seth
	Wiring (HW vs Conn)		Seth/ Chris
	Power Supply		Seth/ Chris
	Lights/LEDs		Seth
	Grd/ EMI Shielding		Seth/ Chris
	Camera		Seth
	LCD		Seth/ Aaron
	SD or USB		Seth & All
	Switches		Seth
	Breadboard Testing		Seth/ Chris

	TASKS		OWNER	MAN Hrs	03-24	03-31	04-07	04-14	04-21	04-28	05-05	05-12	05-19	05-26	06-02	06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08
					EVT					DVT					SAT					Production
Build & Test			Seth
	Build Prototypes/ Test machines		Seth/ Chris					Guava!
	Functional		Seth/ Brent
	Speed		Seth/ Brent
	Mechanical Performance		Seth/ Brent
	Useability		Seth/ Chris
	Environmental		Seth/ Brent
	Op-Shock		Seth/ Brent
	Non-Opshock		Seth/ Brent
	EMC		Seth/ Chris
	Long Term Reliability		Seth/ Brent
Packaging/ Documentation			Steven
	Shipping Foam
	Unbox Manual
	Operation Manual
	Print Profiles
	BOM Creation		Seth
Manufacturing			Chris
	Build SAT machines
	Assembly OHAI Kits		Chris/Robert
	Assembly line Layout		Chris
	PreSubs		Chris
	Cycle time modeling		Chris
	Cycle time verification		Chris
	Optimize MFG process		Chris
	Presub/Sub Test Defined		Chris
	Pre/Sub Test Equip Des/Setup		Chris
	OpenERP Routing		Chris
	Resource Plan		Chris