## Sheet1
Easy TAZ Mini - Work Breakdown Schedule _ v. 3.0
				06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01
				92					49					20				0
TASKS		OWNER	MAN Hrs	EVT2 - Engineering Validation Test / –- Begonia –-					DVT - Design Verification Test / –- Camellia –-					SAT–Design Maturity / Ship Approval Test / –Daffodil-				Production Commences & Inventory Buildup			Product Announcement & Sales start			Cyber Monday
Architect		Seth
Cube or Lulzbot? Decision		Seth
- CAD		Seth
- Build mockups		Seth
- Cost estimate		Seth/ Chris
Electronics- Controller & Comm		TBD
- Research features		Aaron
- Research Market trends		Aaron
- Pros & Cons on FW effort		Aaron
- Final Config/feature proposal		Seth
- Final Config Decision		All
Non-UL/UL Ready/ Full UL?		Seth & All
- Define what need to be done		Seth/ Chris
- Re cost estimate		Seth
Software		Aaron/ Jeff
UI Flow		Aaron/Jeff
UI Design		Aaron/Jeff
Build Core OS/Repo		Aaron/Jeff
USB drive automount		Aaron/Jeff
Wifi		Aaron/Jeff
LED driver		Aaron/Jeff
Web Daemon		Aaron/Jeff
Video		?
		Aaron/Jeff
Video Production		?
Firmware
RAMBO – SD		Aaron/Seth					no longer applied
RAMBO – BBB		Aaron/Seth
RAMBO – EZT HW		Aaron/Seth
Auto Leveling		Aaron/Seth
Code Release		Aaron/Jeff					DVT					SAT
Video Production
Mechanical		Seth
Frame		Seth
X-Axis		Seth
Y-Axis		Seth
Z-Axis		Seth
Extruder		Seth/ Brent
Drive System		Seth
New Spool loc/feed		Seth
LCD Mount		Seth/ Aaron
Motor Selection		Seth
Nozzle Sel/ Design		Seth/ Brent
Heat bed		Seth/ Brent
- PET tape?
- Holding the bed?
Auto Bed Leveling		Seth/ Brent
Electronics/ Electrical		Seth
Mini-RAMBO		Chris
Wiring (HW vs Conn)		Seth/ Chris
Power Supply		Seth/ Chris
Lights/LEDs		Seth
Grd/ EMI Shielding		Seth/ Chris
Camera		Seth					<<<
LCD		Seth/ Aaron
USB		Seth & All
Switches		Seth
Breadboard Testing		Seth

				06-09	06-16	06-23	06-30	07-07	07-14	07-21	07-28	08-04	08-11	08-18	08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01
				92					49					20				0
TASKS		OWNER	MAN Hrs	EVT2 - Engineering Validation Test / –- Begonia –-					DVT - Design Verification Test / –- Camellia –-					SAT–Design Maturity / Ship Approval Test / –Daffodil-				Production Commences & Inventory Buildup			Product Announcement & Sales start			Cyber Monday
Build & Test		Seth
Build Prototypes/ Test machines		Seth/ Chris
Functional		Seth/ Brent
Speed		Seth/ Brent
Mechanical Performance		Seth/ Brent
Useability		Seth/ Chris
Environmental		Seth/ Brent
Op-Shock		Seth/ Brent
Non-Opshock		Seth/ Brent
EMC		Seth/ Chris
Long Term Reliability		Seth/ Brent
Packaging/ Documentation		Steven
Frame available for prototype		Seth
Shipping Foam		Steven					1st Pro
Fed-EX Test		Steven					FedEx
Unbox Manual		Steven
Operation Manual		Steven
Consumer's Open Box Exp Test		Steven
Print Profiles		Seth
BOM Creation		Seth
Procurement		Seth/ Chris
DVT Parts		Seth
SAT		Seth
Production		Seth/ Chris
Risk Purchases Long Lead Items		Seth/ Chris
Plastic		Chris/ Stan
Manufacturing		Chris
Recruiting mfg staffs		Chris
Training new team		Chris
Build SAT machines		Chris
Assembly OHAI Kits		Seth/Robert
Assembly line Layout		Chris
PreSubs		Chris
Cycle time modeling		Chris
Cycle time verification		Chris
Optimize MFG process		Chris
Presub/Sub Test Defined		Chris
Pre/Sub Test Equip Des/Setup		Chris
OpenERP Routing		Chris
Resource Plan		Chris
Marketing & Communications		Harris
Product Design		All
Business Case Development		Harris
Brand and Competitive Analysis		Harris
Goal(s) Articulation		Harris
Strategic Comms. Framework		Harris
Target Audience Identification		Harris
Creative Brief		All
Graphic Approach - Packaging		Harris/Steven
Product Naming		All
Strategic Message Development		All
High-Level Tactical Plan		Harris/Rachael
Product Collateral Design		Harris/Steven
Website-Related Design Recs		Harris/Steven
Reseller Demos		Harris/Rachael