## Sheet1
			LulzBot Mini – Product Development Cycle – v3.32
			08-25	09-01	09-08	09-15	09-22	09-29	10-06	10-13	10-20	10-27	11-03	11-10	11-17	11-24	12-01	12-08	12-15	12-22	12-29	01-05	01-12	01-19
								SA	CES
TASKS		OWNER	EVT / Engineering Verification Test / (Begonia)					DVT/SAT – Qualification / Design Verification/Ship Approval Test / (Camellia / Daffodil)					Production & Inventory Buildup / (Daffodil)
R&D – Mechanical		Seth
Drive rod Wobble		Seth
Hex Nozzles breaking		Brent
Install new nozzles on all C&C printers		Bernt
Fuzzies on Wiper		Brent

R&D Electrical		Seth
ESC Testing		ChrisW
Order parts once testing is complete		Seth
Test new Mini-Rambo when it arrives		ChrisW

Software		Steven
Bug testing		Steven
GUI changes		Steven
Print Profiles		Brent/Steven
Packaging		Steven

Code Release		Steven						DVT/SAT
Build & Test		Seth
Test Plan		Seth/ Chris
Build Prototypes/ Test machines		Seth/ Brent
Functional		Seth/ Brent
Speed		Seth/ Brent						Done
Mechanical Performance		Seth/ Brent
Usability		Seth/ Steven
Environmental		Seth/ Brent						Done
Op-Shock		Seth/ Brent						Done
Non-Opshock		Seth/ Brent						Done
EMC		Seth
Long Term Reliability		Seth/ Stan
Packaging / Documentation		Steven
Machine for foam prototype		Seth
Shipping Foam		Steven						Done
Final Foam design verify		Steven						Done
Internal Drop Test								Done
Fed-EX Test		Steven						Done
Boxes								Done
Operation Manual		Steven
- Quick Start Guide		Steven
Web site pages
Consumer's Open Box Exp Test		Steven
Packing list		Seth
Quality Assurance Record		Seth
Safety guide		Steven
Procurement
Camellia (DVT/SAT) Parts		Seth/ Toni						Done
Production Parts – Long lead		Seth/ Jeff
Production Parts		Toni/Seth						sheet metal, PEI
Plastic		Chris/ Stan						Extended
Manufacturing		Chris
Process step define (presub-FA)		Seth/ Chris	1st pass
Process step layout		Chris
Assembly line layout & BOM		Chris
Mfg line 2 construction/ purchase		Andy/ Chris
Resource Plan proposal/ approval		Chris/ Jeff
Recruiting mfg staffs		Chris
Training new team		Chris
Build DVT/SAT machines		Chris						Crotons
Assembly OHAI Kits		Seth/Robert
PreSub Op setup & production prep		Chris
Cycle time modeling		Chris	1st pass
Cycle time verification/ Opti		Chris						Extended
Optimize MFG process		Chris
Presub/Sub Test Defined		Chris						Done
Pre/Sub Test Equip Des/Setup		Chris
- Harness Test Fixture		Brent
- Other fixtures
MO		Chris
Marketing / PR		Harris
Frame Design		Kevin/Natasha						Done
Customer Survey		Natasha/Harris						Done
Market Research Review		Harris						Done
Product Packaging		Kevin/Natasha						Done
Teaser / Promotional Item		Marketing (All)						Done
Press Engagement		Harris/Schwartz
LulzBot.com/Mini Landing Pg.		Marketing (All)
LulzBot.com/Rocktopus Landing Pg.		Marketing (All)
Reseller Engagement		Rachael/Ben
Product Collateral Design		Kevin/Claudio
CES Launch Prep		Marketing (All)
Final Product Photos		Kevin
Product Description		Harris/Natasha